## Tabelle1
Project Name | Digitales Wartezimmer | [19 empty] | Status Date | [39 empty] | critical path | [23 empty] | O = Owner R = Resources D = Duration in days E = Effort
Project Leader | Aberan Sivalingam | [19 empty] | Base Plan Date | [26 empty] | progress | [12 empty] | non-critical path
Task Name | Calender Week
From - To
| Weekday |  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
| O | R | E | D
1 MongoDB Installieren | Mbau |  | 2 | bar: M to T
2 MongoDB Schema Erstellen | Mbau |  | 2 | bar: W to T
3 NodeJS Installieren | Mbau |  | 1 | bar: F
4 Express Routen Definieren | Mbau |  | 3 | bar: M to W
5 Server Bussiness Logik implementieren | Mbau |  | 4 | bar: T to F
6 DB Schnittstelle Implementieren | Mbau |  | 3 | bar: T to F; M
7 Login UI Implementieren | Asiv Tbaa |  | 3 | bar: W to F
8 Landing Page UI Implementieren | Asiv Tbaa |  | 2 | bar: T to W
9 Praxis UI Implementieren | Tbaa |  | 3 | bar: F; M to T
10 Warteschlangen UI Implementieren | Asiv |  | 3 | bar: F; M to T
11 Server Schnittstelle Implementieren | Asiv Tbaa |  | 5 | bar: M to F
12 Server Schnittstelle mit UI verknüpfen | Asiv Tbaa |  | 5 | bar: M to F
13 Bootstrap installieren | Tbaa |  | 1 | bar: M
14 UI Test | Asiv |  | 2 | bar: M to T
15 Workflow testen | Tbaa |  | 2 | bar: W to T
16 Usabillity testen | Mbau |  | 2 | bar: F; M
Resources
| PS Consulting International |  |  |  | T: phone: +49 (0) 74 56 - 7 95 72-60; S: e-mail: info@psconsult.de; M: Owner = responsible team member (name code) = not more than one person
| Project Management Training & Consulting |  |  |  | T: fax: +49 (0) 74 56 - 7 95 72-66; S: www.psconsult.de; M: Resources = executing team members (name codes) = 1 or more persons
Effort = work effort to finish an activity (i.e. in "hours" or in "person" days)
Duration = elapsed time in days or weeks