## Tabelle1
Project Name | Digitales Wartezimmer | [19 empty] | Status Date | [13 empty] | 2018-05-22 | [25 empty] | critical path | [23 empty] | O = Owner R = Resources D = Duration in days E = Effort
Project Leader | Aberan Sivalingam | [19 empty] | Base Plan Date | [13 empty] | 2018-05-18 | [12 empty] | progress | [12 empty] | non-critical path
Task Name | Calender Week | [10 empty] | KW20 | [6 empty] | KW21 | [6 empty] | KW22 | [6 empty] | KW23 | [6 empty] | KW24 | [6 empty] | KW25 | [6 empty] | KW26
| From - To | [10 empty] | 14.5-18.5 | [6 empty] | 21.5-25.5 | [6 empty] | 28.5-1.6 | [6 empty] | 4.6-8.6 | [6 empty] | 11.6-15.6 | [6 empty] | 18.6-22.6 | [6 empty] | 25.6-29.6
| Weekday |  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
| O | R | E | D
1 MongoDB Installieren | Mbau | Mbau | 2 | 2 | bar: 14.5-18.5 M to 14.5-18.5 T
2 MongoDB Schema Erstellen | Mbau | Mbau | 2 | 2 | bar: 14.5-18.5 W to 14.5-18.5 T
3 NodeJS Installieren | Mbau | Mbau | 1 | 1 | bar: 14.5-18.5 F
4 Express Routen Definieren | Mbau | Mbau | 3 | bar: 21.5-25.5 M to 21.5-25.5 W
5 Server Bussiness Logik implementieren | Mbau | Mbau | 4 | bar: 28.5-1.6 T to 28.5-1.6 F
6 DB Schnittstelle Implementieren | Mbau | Mbau | 3 | bar: 21.5-25.5 T to 21.5-25.5 F; 28.5-1.6 M
7 Login UI Implementieren | Tbaa | Asiv Tbaa | 3 | 2 | bar: 14.5-18.5 W to 14.5-18.5 F
8 Landing Page UI Implementieren | Tbaa | Asiv Tbaa | 2 | bar: 21.5-25.5 T to 21.5-25.5 W
9 Praxis UI Implementieren | Tbaa | Tbaa | 3 | bar: 21.5-25.5 F; 28.5-1.6 M to 28.5-1.6 T
10 Warteschlangen UI Implementieren | Asiv | Asiv | 3 | bar: 21.5-25.5 F; 28.5-1.6 M to 28.5-1.6 T
11 Server Schnittstelle Implementieren | Tbaa | Asiv Tbaa | 5 | bar: 4.6-8.6 M to 4.6-8.6 F
12 Server Schnittstelle mit UI verknüpfen | Tbaa | Asiv Tbaa | 5 | bar: 11.6-15.6 M to 11.6-15.6 F
13 Bootstrap installieren | Tbaa | Tbaa | 1 | 1 | bar: 14.5-18.5 M
14 UI Test | Asiv | Asiv | 2 | bar: 18.6-22.6 M to 18.6-22.6 T
15 Workflow testen | Tbaa | Tbaa | 2 | bar: 18.6-22.6 W to 18.6-22.6 T
16 Usabillity testen | Mbau | Mbau | 2 | bar: 18.6-22.6 F; 25.6-29.6 M
Resources
| PS Consulting International |  |  |  | 21.5-25.5 T: phone: +49 (0) 74 56 - 7 95 72-60; 11.6-15.6 S: e-mail: info@psconsult.de; 25.6-29.6 M: Owner = responsible team member (name code) = not more than one person
| Project Management Training & Consulting |  |  |  | 21.5-25.5 T: fax: +49 (0) 74 56 - 7 95 72-66; 11.6-15.6 S: www.psconsult.de; 25.6-29.6 M: Resources = executing team members (name codes) = 1 or more persons
Effort = work effort to finish an activity (i.e. in "hours" or in "person" days)
Duration = elapsed time in days or weeks